## rules_of_scrum_2020
| Section | Principle
1 | The Basic Scrum Process | Every Sprint is the Same Length
2 | The Basic Scrum Process | Every Sprint is Four Weeks or Less in Duration
3 | The Basic Scrum Process | There are no Breaks Between Sprints
4 | The Basic Scrum Process | The Intention of Every Sprint is Potentially Shippable Software
5 | The Basic Scrum Process | Every Sprint includes Sprint Planning
6 | The Basic Scrum Process | The Sprint Planning Meeting is Timeboxed to 2 Hours / Week of Sprint Length
7 | The Basic Scrum Process | Every Sprint includes Sprint Review for stakeholder feedback on the product
8 | The Basic Scrum Process | Every Sprint includes Sprint Retrospective for the team to inspect and adapt
9 | The Basic Scrum Process | Review and Retrospective meetings are timeboxed in total to 2 hours / week of Sprint length
10 | The Basic Scrum Process | There is no break between Sprint Review and Retrospective meetings
11 | The Basic Scrum Process | The Daily Scrum is timeboxed to 15 minutes
12 | The Basic Scrum Process | The Daily Scrum occurs every day at the same time of day
13 | The Basic Scrum Process | Team Members answer only three questions at the Daily Scrum (no discussion)
14 | The Basic Scrum Process | The scope of work for a Sprint is never expanded mid-Sprint (interruptions)
15 | The Basic Scrum Process | All stakeholders are invited to attend the demo portion of the Sprint Review
16 | The Basic Scrum Process | PBIs have their effort estimated collectively by the team who will be implementing them
17 | The Basic Scrum Process | The Scrum Team is no less than five people and no more than eleven people
18 | The Basic Scrum Process | The Scrum Team includes the Product Owner, ScrumMaster and the Team Members
19 | The Basic Scrum Process | The Scrum Team does not include any other people (e.g. a manager who doesn't do tasks)
20 | The rules of Scrum related to the Product Backlog | No two Product Backlog Items (PBIs) have the same position in the Product Backlog (ordered)
21 | The rules of Scrum related to the Product Backlog | All PBIs are related to a single product (or system)
22 | The rules of Scrum related to the Product Backlog | PBIs are ordered by expected Value (ROI, NIAT, etc)
23 | The rules of Scrum related to the Product Backlog | PBIs are slices through our system (features or functions)
24 | The rules of Scrum related to the Product Backlog | PBIs are written as User Stories (As a ___ I can ___ so that ___)
25 | The rules of Scrum related to the Product Backlog | The top PBIs are small enough (effort) that several can fit into a single Sprint
26 | The rules of Scrum related to the Product Backlog | PBIs are invitations to conversations, not detailed specifications
27 | The rules of Scrum related to the Product Backlog | Known defects (external quality) generally are ordered at the top of the Product Backlog to be fixed in the next Sprint
28 | The rules of Scrum related to the Product Backlog | The Product Backlog is refined to ensure it is ready for every Sprint Planning meeting
29 | The rules of Scrum related to the Product Backlog | Any stakeholder (e.g. Team Member, salesperson, client) can suggest a new PBI
30 | The rules of Scrum related to the Product Backlog | The Product Backlog is easily visible to every stakeholder (e.g. cards on a wall or an electronic tool with open access)
31 | The rules of Scrum related to the Team Member Role | I use Scrum as a tool for product development
32 | The rules of Scrum related to the Team Member Role | I am truthful about the internal quality of my product (technical debt)
33 | The rules of Scrum related to the Team Member Role | I work with only one Scrum team
34 | The rules of Scrum related to the Team Member Role | I am a full-time member of that team (no non-Team Member duties)
35 | The rules of Scrum related to the Team Member Role | I know my product well and can quickly describe its high-level purpose
36 | The rules of Scrum related to the Team Member Role | I know my product well and can quickly describe its high-level architecture
37 | The rules of Scrum related to the Team Member Role | I actively seek to help my team mates
38 | The rules of Scrum related to the Team Member Role | I commit myself to doing whatever it takes to reach each and every Sprint goal
39 | The rules of Scrum related to the Team Member Role | I volunteer for a new task from the Sprint backlog as soon as I complete a task
40 | The rules of Scrum related to the Team Member Role | I share my obstacles (technical, tools, process, teamwork, personal) every Daily Scrum
41 | The rules of Scrum related to the Team Member Role | I am willing to learn any skill needed to help my team
42 | The rules of Scrum related to the Team Member Role | I work with all the team members to expand the Definition of Done
43 | The rules of Scrum related to the Team Member Role | I take direction for product vision and scope from my team's Product Owner
44 | The rules of Scrum related to the Team Member Role | I live the values and principles of the Agile Manifesto in my team
45 | The rules of Scrum related to the Team Member Role | I attend every Sprint Planning meeting in person
46 | The rules of Scrum related to the Team Member Role | I attend every daily Scrum Meeting in-person
47 | The rules of Scrum related to the Team Member Role | I attend every Sprint Review Meeting in-person
48 | The rules of Scrum related to the Team Member Role | I attend every Sprint Retrospective Meeting in-person
49 | The rules of Scrum related to the Team Member Role | I never tell any other individual team member which task to work on next
50 | The rules of Scrum related to the Team Member Role | No member of my team reports to me
51 | The rules of Scrum related to the Team Member Role | I do not track my hours or my actual time on tasks
52 | Rules of Scrum related to the Product Owner role | Your Product Owner is truthful about the condition of the product (its value scope and costs)
53 | Rules of Scrum related to the Product Owner role | Your Product Owner uses the Sprint Review to help the team continuously improve the product
54 | Rules of Scrum related to the Product Owner role | Your Product Owner has no duties outside the Product Owner duties
55 | Rules of Scrum related to the Product Owner role | Your Product Owner is knowledgable about the product and the business
56 | Rules of Scrum related to the Product Owner role | Your Product Owner can veto the inclusion of an idea on the Product Backlog
57 | Rules of Scrum related to the Product Owner role | Your Product Owner refines the Product Backlog so it is ready for each Sprint Planning Meeting
58 | Rules of Scrum related to the Product Owner role | Your Product Owner is allowed to communicate directly with any stakeholder of the Team
59 | Rules of Scrum related to the Product Owner role | Your Product Owner is the sole and final decision-maker for when the Team's work is released to production, users or customers
60 | Rules of Scrum related to the Product Owner role | Your Product Owner knows if the estimated financial return of the work of a Sprint is higher than its estimated cost
61 | Rules of Scrum related to the Product Owner role | Your Product Owner has the bandwidth and capacity to respond to the Team's questions within minutes
62 | Rules of Scrum related to the Product Owner role | Your Product Owner never does hands-on technical work with the Team
63 | Rules of Scrum related to the Product Owner role | Your Product Owner never tells the Team how to solve a technical problem
64 | Rules of Scrum related to the Product Owner role | Your Product Owner always lets the Team freely decide how many Product Backlog Items to do in a Sprint
65 | Rules of Scrum related to the Product Owner role | Your Product Owner never interrupts the team mid-Sprint with new “high priority” Product Backlog Items
66 | Rules of Scrum related to the Product Owner role | Your Product Owner puts known defects at the top of the Product Backlog
67 | Rules of Scrum related to the Product Owner role | Your Product Owner creates and maintains the Team's product Â or release burndown chart
68 | Rules of Scrum related to the ScrumMaster role | Your ScrumMaster is truthful about the condition of the team and the Scrum process
69 | Rules of Scrum related to the ScrumMaster role | Your ScrumMaster believes that Scrum will help the team improve
70 | Rules of Scrum related to the ScrumMaster role | Your ScrumMaster uses the Retrospective to help your team improve its processes and teamwork
71 | Rules of Scrum related to the ScrumMaster role | Your ScrumMaster works with only one Scrum Team
72 | Rules of Scrum related to the ScrumMaster role | Your ScrumMaster has no duties outside of the ScrumMaster duties
73 | Rules of Scrum related to the ScrumMaster role | Your ScrumMaster knows Scrum well and can explain it both quickly and in detail to others
74 | Rules of Scrum related to the ScrumMaster role | Your ScrumMaster has final authority within the team on the correct way to use the Scrum Process
75 | Rules of Scrum related to the ScrumMaster role | Your ScrumMaster can enforce timeboxes within the team (e.g. meetings)
76 | Rules of Scrum related to the ScrumMaster role | Your ScrumMaster is allowed to communicate directly with any stakeholder of the team
77 | Rules of Scrum related to the ScrumMaster role | All people outside the team know that it is the ScrumMaster’s job to shield the team from interruptions
78 | Rules of Scrum related to the ScrumMaster role | Your ScrumMaster is empowered to immediately remove in-team obstacles
79 | Rules of Scrum related to the ScrumMaster role | Your ScrumMaster is expected to work diligently to remove organizational obstacles
80 | Rules of Scrum related to the ScrumMaster role | Your ScrumMaster has the bandwidth and capacity to respond within minutes to the team’s questions
81 | Rules of Scrum related to the ScrumMaster role | Your ScrumMaster consistently avoids doing hands-on technical work with the team
82 | Rules of Scrum related to the ScrumMaster role | Your ScrumMaster never tells the team how to solve a technical problem
83 | Rules of Scrum related to the ScrumMaster role | Your ScrumMaster helps the team expand the definition of “done”
84 | Rules of Scrum related to the ScrumMaster role | Your ScrumMaster creates and maintains the team’s Sprint burndown chart

## Sheet1
http://www.agileadvice.com/rules-of-scrum/